**PTTC Supplement Subgroup Agenda, September 14, 2021 4:00 – 5:00pm EST.**

|  |  |  |
| --- | --- | --- |
| **Time**  **(Eastern Time)** | **Topic** | **Speaker/Facilitator** |
| 4:00 | Introductions | Van Wilson, DID working group |
| 4:10 | Environmental Scan update | NCO |
| 4:15 | Budget and Narrative discussion  Due 10/30, per NOA |  |
| 4:25 | Project Planning | Van Wilson, All |

**Draft Timeline:**

Phase 1: Sept 2021 - Dec 2021: **Creating Survey and Interview Protocol (sampling)**  
Phase 2: January, 2022: **Deploy Survey & Conduct Interviews**  
Phase 3: February 2022: **Code & Compile Data**  
Phase 4: March, 2022: **Write report**  
March 31, 2022: **report due to SAMHSA**

**PTTC Supplemental Grant Activities:**

**PFS Cohort Assessment:** The Strategic Prevention Framework Partnerships for Success (PFS) grants have provided funding to states, tribes, territories, Pacific Jurisdictions, and communities to prevent the onset and reduce the progression of substance abuse and its related problems while strengthening prevention capacity and infrastructure at the community and state level. The program is intended to address one of the nation’s top substance abuse prevention priorities. Grant recipients identify the primary problematic substances in their jurisdictions and develop and implement strategies to prevent the misuse of these substances among youth and adults.  Since its inception, PFS programming has varied in grant recipients, funding levels, and substance targets. We would like to develop and implement a descriptive framework for understanding PFS cohort requirements, accomplishments, and contextual factors that impact PFS success. This would include a plan/strategy for the PTTCS to work with PFS grant recipients in their regions to conduct an analysis of the strengths, weaknesses, including those related to program data collection and reporting requirements, develop lessons learned, and establish programmatic recommendations based upon findings from each of these cohort variations**.  T**his assessment will help inform future funding announcements.